### WOOD END - Climate Action Plan

#### 1. Staff Expertise

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Enhance staff knowledge on climate change and sustainability | 1. Organise annual climate and sustainability training sessions for staff. 2. Provide access to online courses/webinars related to energy efficiency and climate education (National College) 3. Develop internal knowledge-sharing sessions to disseminate best practises. | Headteacher / CPD Coordinator | - Budget for training - Access to online platforms - Time allocated for CPD | - 80% staff complete at least one training annually - Staff demonstrate increased confidence in delivering climate education - Staff incorporate sustainability practises in daily routines | Climate education and green careers |
| Build capacity to support energy efficiency initiatives | 1. Train site staff on energy monitoring and maintenance of energy-saving equipment. 2. Develop a checklist for energy efficiency best practises in school operations. | Site Manager / Facilities Lead | - Training materials - Time for training sessions - Energy monitoring tools | - Reduction in energy waste incidents - Improved maintenance of energy systems - Energy consumption data shows improvement | Decarbonisation |

#### 2. Staff/Pupils

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Foster a culture of sustainability among pupils and staff | 1. Launch an Energy Savers programme involving pupils and staff. 2. Run regular sustainability-themed assemblies and workshops. 3. Promote energy-saving behaviours (e.g., switching off lights, reducing heating use). | Sustainability Lead / Year Group Leaders | - Educational materials - Time for assemblies/workshops - Incentives for Energy Savers - GEM for being Green | - Active participation of at least 20% of pupils - Observable behaviour changes in energy use - Positive feedback from staff and pupils - GEMS awarded | Climate education and green careers |
| Empower pupils to understand and reduce their carbon footprint | 1. Integrate simple carbon footprint activities in class projects. 2. Organise eco-themed competitions and challenges. | Class Teachers / Sustainability Lead | - Curriculum resources - Prizes for competitions | - Increased pupil awareness measured through surveys - Participation in eco-competitions - Pupils demonstrate understanding of personal impact | Climate education and green careers |

#### 3. Buildings/Grounds

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Improve energy efficiency of the school building | 1. Conduct an energy audit to identify further energy-saving opportunities. 2. Optimise heating schedules and controls based on occupancy. 3. Ensure solar panels are operating with maximum efficiency. | Site Manager / Business Manager | - External energy audit service - Heating system controls - Funding for solar installation | - Energy rating maintains at B - Reduced energy bills - Increased renewable energy generation onsite | Decarbonisation |
| Enhance biodiversity and outdoor learning spaces | 1. Develop existing green spaces with native plants and wildlife habitats. 2. Create planters and flower beds for pupil engagement. 3. Forest schools developed with a sustainability lens | Grounds Staff / Curriculum Lead | - Plants and gardening tools - Outdoor seating - Volunteer support | - Increased biodiversity indicators (e.g., bird/insect sightings) - Regular use of outdoor learning spaces - Positive pupil engagement with nature | Biodiversity |

#### 4. School Lunches

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Promote sustainable and healthy school meals | 1. Increase plant-based meal options on the menu. (Green Tuesday) 2. Source food locally to reduce food miles. 3. Educate pupils on the environmental impact of food choices. 4. Have this as a key element of the procurement of new catering provider | Catering Manager / PSHE Lead | - Supplier contracts - Educational materials - Menu planning support | - Increase in plant-based meal uptake by 20% - Local food percentage increased - Pupils demonstrate awareness of food sustainability | Climate education and green careers |

#### 5. Curriculum

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Embed climate change and sustainability across the curriculum | 1. Review and update curriculum plans to include climate topics in science, geography, and literacy. 2. Use project-based learning focused on local environmental issues. 3. Train teachers on delivering climate-related content effectively. | Curriculum Lead / Subject Leaders | - Curriculum resources - CPD sessions (National College) - Collaboration time | - Climate topics integrated across key stages - Pupils complete climate-focused projects - Teacher confidence and competence improved | Climate education and green careers |

#### 6. Wellbeing

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Support pupil and staff wellbeing through connection with nature | 1. Increase time spent outdoors through lessons and breaks. 2. Develop mindfulness and wellbeing activities in green spaces. 3. Promote walking and active travel to school. (Big Walk and Wheel/ Safe and Active Schools Award) 4. Replace the bike/scooter store so it is a more attractive option | Wellbeing Lead / PE Coordinator | - Outdoor learning resources - Mindfulness materials (My Happy Mind) - Safe walking routes information | - Increased outdoor activity time - Positive wellbeing survey results - Uptake in active travel modes | Adaptation and resilience |

#### 7. Opportunities for Pupil Leadership

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Develop pupil leadership in climate action | 1. Establish an Eco Committee with pupil representatives. 2. Support pupils to lead sustainability projects and campaigns. 3. Provide training and resources for pupil leaders. | Sustainability Lead / Year Group Leaders | - Meeting space - Training materials - Budget for projects | - Active Energy Savers meetings - Completed pupil-led projects - Increased pupil engagement in sustainability | Climate education and green careers |

#### 8. Procurement

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Ensure sustainable procurement practices | 1. Review procurement policies to prioritise eco-friendly products and suppliers. 2. Source cleaning and office supplies with low environmental impact. 3. Monitor and report on procurement sustainability annually. | Business Manager / Procurement Officer | - Updated procurement policy template - Supplier information - Monitoring tools | - Procurement policy updated and implemented - Increased percentage of sustainable products purchased - Annual sustainability procurement report produced | Decarbonisation |

#### 9. Parents

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Engage parents in the school’s climate action efforts | 1. Communicate climate initiatives through newsletters and social media. 2. Organise family eco-events and workshops. 3. Encourage sustainable travel and behaviour at home. | Parent Liaison / Sustainability Lead | - Communication channels - Event materials - Volunteer support | - Increased parent attendance at eco-events - Positive parent feedback - Evidence of sustainable behaviours at home | Climate education and green careers |

#### 10. Transportation and Travel

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Reduce carbon emissions from school travel | 1. Promote use of public transport and walking routes. 2. Implement a safe scoot-to-school scheme. 3. Monitor and report on travel modes annually. | Travel Coordinator / PE Lead | - Maps of safe routes - Promotional materials - Monitoring tools | - Increased percentage of pupils using active/public transport - Walking bus scheme operational - Annual travel report showing improvements | Decarbonisation |

#### 11. Digital Sustainability

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Promote energy-efficient digital practices | 1. Encourage staff and pupils to power down devices when not in use. 2. Implement energy-saving settings on all school IT equipment. 3. Review digital infrastructure for efficiency improvements. | IT Manager / Sustainability Lead | - IT policy updates - Energy management software - Training materials | - Reduction in energy use from IT equipment - Staff and pupils follow digital sustainability guidelines - IT infrastructure optimised for energy efficiency | Decarbonisation |

#### 12. Partnerships and Collaborations

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Build partnerships to enhance climate action | 1. Collaborate with local environmental organisations for projects and resources. 2. Engage with local authority sustainability initiatives. 3. Participate in regional climate networks for schools. | Headteacher / Sustainability Lead | - Contact lists - Partnership agreements - Transport for visits | - Established partnerships with at least two local organisations - Participation in local climate initiatives - Shared resources and joint projects completed | Climate education and green careers |

#### 13. Governance and Policy

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Integrate climate action into school governance | 1. Develop a formal climate change policy for the school. 2. Include climate action updates in governing body meetings. 3. Set measurable targets for energy reduction and sustainability. | Chair of Governors / Headteacher | - Policy templates - Meeting agendas - Monitoring tools | - Climate policy approved and published - Regular reporting to governors - Progress against targets demonstrated annually | Decarbonisation |
| Ensure compliance with relevant environmental legislation | 1. Review school compliance with environmental regulations. 2. Train relevant staff on compliance requirements. | Business Manager / Site Manager | - Regulatory guidance - Training resources | - No compliance breaches - Staff aware of legal obligations | Adaptation and resilience |

#### 14. Resilience and Adaptation

| Objective | Actions | Person responsible | Resources needed | Success criteria | DfE Area |
| --- | --- | --- | --- | --- | --- |
| Prepare the school for climate-related risks | 1. Review and update the school’s emergency and flood risk plans. 2. Assess building resilience to extreme weather (e.g., heat, storms). 3. Implement measures to improve indoor air quality and thermal comfort. | Site Manager / Health & Safety Lead | - Risk assessment tools - Emergency plan templates - Budget for adaptations | - Updated emergency plans in place - Adaptations completed to improve resilience if necessary - Positive feedback from staff and pupils on comfort | Adaptation and resilience |

This plan is designed to be practical and tailored to the urban primary school setting of Dordon, considering current good practises and opportunities for development within the OFSTED framework.